## Master Plan
Accenture/9Lenses Master Plan
|  | Owner | Status | Target Completion Date | Next Activity / Notes
1 | Asset Digitization
| 1.1 Develop digitization process | 9L | In Progress
| 1.2 Prioritize assets | Accenture/9L
| 1.3 Configure Assets | 9L
1.3.1 See Digitization Progress tab
2 | Marketing Plan
2.1 Create Marketing Strategy
2.1.1 Create brand for centralized IP & capability (Ex. Accenture Diagnostics)
2.1.2 Create metrics and measures of success
2.1.3 Develop staff plan, resources and budget
2.1.4 Create product feedback loop to 9Lenses
2.2 Develop Promotional Materials and Practice-Specific Enablement (videos, collateral, webs assets etc.)
2.3 Create Marketing Communication Messages to Accenture Staff (practice specific)
2.4 Leverage Marketing Communication Channels to Accenture Staff (ex. Intranet, newsletters, sales training)
2.5 Launch External Integrated Marketing Campaign
2.5.1 Develop microsite or Accenture website "homebase"
2.5.2 Develop multi-touch email promotion
2.5.3 Develop social media messages and calendar for promotion
2.5.4 Create digital and print ads
2.5.5 Include collateral, plan in conference materials
2.5.6 Utilize 3rd party resources like YouTube, G2Crowd, Capterra
3 | Sales/Adoption
3.1 Determine regular cadence for reviewing sales metrics
3.2 Assign sales targets & quotas by practice (and region?)
4 | Standup COE
4.1 Product Training
4.2 Process for deployment ordering & billing
4.3 Establish 9L/COE interaction model (Technical Support, Q&A, Best practices)

## Digitization Sched
| 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12 | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 | 2017-07-17 | 2017-07-24 | 2017-07-31 | 2017-08-07 | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04
| WK1 | WK2 | WK3 | WK4 | WK5 | WK6 | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30
Asset 1
Owner Name
SME
Digitization | bar: 2017-02-13
Review 1 | bar: 2017-02-20
Iteration 1 | bar: 2017-02-20
Review 2 | bar: 2017-02-27
Iteration 2 | bar: 2017-02-27
Final Review | bar: 2017-03-06
Sign Off | bar: 2017-03-13
Asset 2
Owner Name
SME
Digitization | bar: 2017-02-13
Review 1 | bar: 2017-02-20
Iteration 1 | bar: 2017-02-20
Review 2 | bar: 2017-02-27
Iteration 2 | bar: 2017-02-27
Final Review | bar: 2017-03-06
Sign Off | bar: 2017-03-13
Asset 3
Owner Name
SME
Digitization | bar: 2017-03-27
Review 1 | bar: 2017-04-03
Iteration 1 | bar: 2017-04-03
Review 2 | bar: 2017-04-10
Iteration 2 | bar: 2017-04-10
Final Review | bar: 2017-04-17
Sign Off | bar: 2017-04-24

## Digitization Progress
Asset Digitization Progress |  |  | T&O
Advanced Customer Strategy
Operations & Procurement
Financial Services
Other
Asset Queue | In Design | Design Approved | In Configuration | In UAT | Completed/Approved
Wave 1 + Pre-Wave 1 Assets
ZBB front office assessment & benchmarks (Excel-based, content in development) | Digital Finance Diagnostic | High Performance Sales Force Assessment (HPSFA) |  |  | HR360
Risk Transformation: Enterprise Risk Management Diagnostic | Finance Transformation: Finance Enterprise Value Targeting |  |  |  | Workforce of the Future
Regulatory & Compliance: Compliance Risk Management Framework | Digital Value Add |  |  |  | HR Time Distribution
Cyber Risk & Resilience: Fraud Diagnostic | RPA Process Evaluator |  |  |  | Performance Management
Financial Risk Management: Credit Risk | HC CAM |  |  |  | HRIS Vendor Scorecard
Coaching Maturity Model |  |  |  |  | Procurement Mastery
HR Estimators |  |  |  |  | OVT
Progress Report on Process Design | [5 empty] | 22
PLP
mPLP ¦ changePLP (Variants of PLP)
Leadership 360
Executive Assimilation
Organization Health Value Assessment
Desired Cultural Assessment
Digital ROAD (rapid org alignment)
Source to Separate :- lifecycle of Employee - No existing asset
Pulse checks
Supply Chain Operating Model assessment
ZBB Supply Chain
Supply Chain digitalization index
IT Capability Maturity Model
Journey to Cloud (J2C)
Accenture Wave 2
Digital readiness assessment | [5 empty] | 14 | 11
Sizing & benchmarking of org
Global consumer pulse research (dependent on timing of rollout)
B2B Customer Experience
Growth Strategy: Market Disruption and Customer Value Survey
Digital Intensity/Customer Engagement (DICE) Index (check with Olivier)
Enterprise Value Targeting (Finance Benchmarking)
Finance Mastery Scales
Shared Services Business Case
Compliance Risk Framework Mastery Scales
3LOD Process Model?
Accenture Regulatory Compliance Platform (Diagnose and Discover portion)
Assessment of 3PL (3rd party logistics) companies
Voice of the customer (Supply Chain performance)
Accenture New Ideas
Customer Experience and Customer Channels Baseline | [5 empty] | 11
Digital Performance Index (DPI)
Vital Signs Model
Fraud Diagnostic
AML Health Check
Vulnerability Assessments
Trade Surveillance
Compliance & Ops Risk Metrics library
Enterprise Risk Management Diagnostic
Product segmentation
Service strategy (Customer segmentation)
Other Assets being considered for 9Lenses Platform
Talent Development Maturity | [5 empty] | 9
Digital Manufacturing Diagnostic
Metrics & Reporting Diagnostic
Robotics & Automation Needs Analysis
Op Model

## Strategy
Accenture Assessments & Diagnostics on 9L |  |  | Assets already on 9Lenses Platform
Assets being considered for 9Lenses Platform*
Accenture Wave 1*
Accenture Wave 2
Accenture New Ideas
*9L in active discussions with owners of 2 assets that appear in Wave 1
T&O-UPDATED | Supply Chain & Ops | Health Strategy | Advanced Customer Strategy | Finance & Ent.
Assets Already on 9Lenses Platform
HR360 | Procurement Mastery | Accountable Care Maturity | High Performance Sales Force Assessment (HPSFA) | Digital Finance Diagnostic
Workforce of the Future | OVT
HR Time Distribution
Performance Management
HRIS Vendor Scorecard
Coaching Maturity Model
Assets being considered for 9Lenses Platform
Talent Development Maturity | Digital Manufacturing Diagnostic | Op Model |  | Metrics & Reporting Diagnostic | 9
Executive Assimilation |  |  |  | Robotics & Automation Needs Analysis
Leadership 360
Leadership Assessment (PLP)
Accenture Wave 1
HC CAM | Supply Chain Operating Model assessment |  | ZBB front office assessment & benchmarks (Excel-based, content in development) | Finance Transformation: Finance Enterprise Value Targeting | 22
HR Estimators | ZBB Supply Chain |  | High-Performance Sales Force Analytics (HPSFA) Assessment | Risk Transformation: Enterprise Risk Management Diagnostic
Progress Report on Process Design | Supply Chain digitalization index |  |  | Regulatory & Compliance: Compliance Risk Management Framework
PLP |  |  |  | Cyber Risk & Resilience: Fraud Diagnostic
mPLP ¦ changePLP (Variants of PLP) |  |  |  | Financial Risk Management: Credit Risk
Leadership 360
Executive Assimilation
Organization Health Value Assessment
Desired Cultural Assessment
Digital ROAD (rapid org alignment)
Source to Separate :- lifecycle of Employee - No existing asset
Pulse checks
Accenture Wave 2
Digital readiness assessment | Assessment of 3PL (3rd party logistics) companies |  | Global consumer pulse research (dependent on timing of rollout) | Enterprise Value Targeting (Finance Benchmarking) | 14 | 11
Sizing & benchmarking of org | Voice of the customer (Supply Chain performance) |  | B2B Customer Experience | Finance Mastery Scales
|  |  | Growth Strategy: Market Disruption and Customer Value Survey | Shared Services Business Case
|  |  | Digital Intensity/Customer Engagement (DICE) Index (check with Olivier) | Compliance Risk Framework Mastery Scales
3LOD Process Model?
Accenture Regulatory Compliance Platform (Diagnose and Discover portion)
Accenture New Ideas
| Product segmentation |  | Customer Experience and Customer Channels Baseline | Fraud Diagnostic | 11
| Service strategy (Customer segmentation) |  | Digital Performance Index (DPI) | AML Health Check
|  |  | Vital Signs Model | Vulnerability Assessments
Trade Surveillance
Compliance & Ops Risk Metrics library
Enterprise Risk Management Diagnostic

## Digital
Accenture Assessments & Diagnostics on 9L |  |  | Assets already on 9Lenses Platform
Assets being considered for 9Lenses Platform
Accenture Wave 1
Accenture Wave 2
Accenture New Ideas
Analytics Advisory | Interactive | Health & Public Service
Assets Already on 9Lenses Platform
Operating Model | Digital Customer Service Diagnostic
Functional Capabilities
Entities
Investment Portfolio
Assets being considered for 9Lenses Platform
Analytics Talent Assessment |  | Multiple
Accenture Wave 1
Accenture Wave 2
Accenture New Ideas

## Technology
Accenture Assessments & Diagnostics on 9L |  | Assets already on 9Lenses Platform
Assets being considered for 9Lenses Platform
Accenture Wave 1
Accenture Wave 2
Accenture New Ideas
SFDC/Cloud First | Workday/Cloud First | SAP
Assets Already on 9Lenses Platform
Change Readiness
Assets being considered for 9Lenses Platform
Strategy Assessment | Change Readiness | Capabilities Assessment
| Global Design Process | Blue Print
| Strategic Readiness Assessment | Roadmapping
Accenture Wave 1
Accenture Wave 2
Accenture New Ideas

## Consulting
Accenture Assessments & Diagnostics on 9L |  |  | Assets already on 9Lenses Platform
Assets being considered for 9Lenses Platform
Accenture Wave 1
Accenture Wave 2
Accenture New Ideas
Resources Supply Chain | Energy | Retail | Infrastructure
Assets Already on 9Lenses Platform
Digital Supply Chain
Market research
Assets being considered for 9Lenses Platform
| Total Talent Assessment | Operating Model | Infrastructure Assessment
Accenture Wave 1
Accenture Wave 2
Accenture New Ideas

## Internal
Accenture Assessments & Diagnostics on 9L | Assets already on 9Lenses Platform
Assets being considered for 9Lenses Platform
Accenture Wave 1
Accenture Wave 2
Accenture New Ideas
Marketing Research
Assets Already on 9Lenses Platform
Digital Portal User Experience
Assets being considered for 9Lenses Platform
Accenture Wave 1
Accenture Wave 2
Accenture New Ideas
Internal functions

## Client Specific
Accenture Assessments & Diagnostics on 9L |  | Assets already on 9Lenses Platform
Client Specific Assets
Asset | Client
Assets Already on 9Lenses Platform
HR Modernization | Walmart
Talent Acquisition Assessment | J&J
Candidate Experience | J&J
Global Integrated Operations | Rio Tinto
PTT Leadership Assessment | Xcel Energy
TV & Internet Customer Experience | Comcast
Digital Transformation | Deutsch Telekom
Strategic Priorities | National Grid